## product backlog
Product backlog id | Priority | User Story id | User Story | Scrum Team Assigned | Status | Remark
1 | High | User001 | User Registration | Asmit | Completed | NA
2 | Medium | User002 | User Login | Deepak | Completed | NA
3 | Low | User003 | Flight Booking | Anusha | Completed | NA
4 | High | User004 | Notification | Ashish | Progress | NA
5 | High | User005 | Payment | govind | Completed | NA
6 | High | User006 | Transaction management | Darshan | Progress | NA
7 | High | User007 | Cancelling | Anuradha | Progress | NA
8 | Medium | User008 | Search Flights | Rajesh | Progress | NA
9 | High | User009 | Rewards | Suresh | Not yet | NA
10 | High | User010 | Reviews | jayashree | completed | NA
11 | Medium | User011 | Location Preference | Pranathi | Completed | NA
12 | Medium | User012 | Support | Jyotsna | Progress | NA
13 | High | User013 | Admin | Anisha | Progress | NA

## sprint backlog 1
User Story ID | USER STORY NAME | USER STORY STEP DEFINITION | ASSIGNED TO | ESTIMATED TIME | Actual Time | Status
User001 | User registration | As a user I can provide my email id, phone no., password, username, gender, DOB for registration | Asmit | 10 hrs | 6 hrs | Complete
Verify the email and phone no. using OTP
After successful registration the user is navigated to the home screen
User002 | Login | As a registered user I can able to login into system | Deepak | 8 hrs | 6 hrs | Complete
As a registered user I can login and see the list of movies
As a registered user I can login and filter the flights based on ticket price
User003 | Search Flights | As a user I want to search for available flights, so that I can implement booking API | jayashree | 6 Hrs | 4 hrs | Complete
As a user I want to search for available flights, so that I can implement search form validation
User004 | Notifications | As a user I want to receive notifications about my bookings, so that I am informed of any changes | Anuradha | 8 hrs | 6 hrs | Completed
User005 | Payment | As a user I can enter the card details | Anusha | 8 hrs | 5 hrs | Complete
As a user I can do the payment
As a user I can check flight booking confirmed after payment
User006 | Transaction Management | As a user, I want to manage my payment transactions easily and securely | Jyotsna | 6 hrs | 4 hrs | Complete
As a user, I want a transparent breakdown of all charges and fees associated with flight booking

## sprint backlog 2
USER STORY ID | USER STORY NAME | USER STORY STEP DEFINITION | ASSIGNED TO | ESTIMATED TIME | Actual Time | Status
user007 | ticket booking | As a user i can search the flight name from the search bar | govind | 11 hrs | 6 hrs | completed
user008 | choose location | As a user i can choose destination location to plan a trip |  | 8 hrs | 6 hrs | Completed
user009 | seat selection | As a user i can select the seat number through selecting section | Asmit | 10 hrs | 4 hrs | complete
user010 | checking rewards | As a user i can check for the rewards so i can take advantage of special offers | Anuradha | 9 hrs | 5 hrs | Progress
user011 | checking reviews | As a user i can check and give the reviews | Anusha | 5 hrs | 4 hrs | Progress
user012 | Reviews | As user a user i can see flight reviews and then i can book according | Darshan | 8 hours | 7 hours | Progress
As a user I book flights according to the ratings
user013 | Admin Dashboard | Admin manages filght Listing | Anisha | 4 hours | 3.5 hours | Progress
|  | Admin checks users |  | 3 hours
|  | Admin checks payment status |  | 5 hours |  | Completed
User014 | Offers on booking | Offers can attract cutomers so i can ask payment partners to show some offers | Rajesh | 4 hours | 3 hours
User015 | Rewards | discount on bookings
User016 | Booking Confirmation | As a user, I want to receive a confirmation of my flight booking, so that i have proof of my reservation | Pranathi | 4 hours | 5 hours | completed

## defect tracking
defect id | defects | created on | creator | assigned to | severity | defect id | defects
d001 | user authentication not working properly | 2024-03-12 | Anisha | Praveen | High | High | closed
d002 | Search bar not working properly | 2024-04-23 | Ravi | Manish | Medium | Medium | closed
d003 | after clicking payment, page is not redirected to payment portal | 2024-04-22 | Mahesh | John | High | High | open
d004 | Order history is not showing | 2024-05-21 | Suresh | Ram | High | Medium | closed
d005 | unable to choose to boarding and destination point | 2024-04-11 | Priyan | Anusha | High | High | open
d006 | Admin dashboard is not showing user activity | 2024-03-09 | Alex | Rudra | High | Medim | open
d007 | cancel button is not working | 2024-04-10 | Andrew | Mohan | Medim | High | closed
d008 | defect while saving user reviews | 2024-05-15 | Peter | Raj | Low | Low | open
d009 | Mandatory fields not working | 2024-03-23 | Abdul | Vinay | low | High | open
d010 | Issue with session timeout | 2024-07-01 | Chaitra | Sushant | Medium | Medium | open